## Dashboard
Franchise Rollout Dashboard
Per-store readiness · per-region rollup · per-checkpoint compliance · v2.0 · Investor-ready
PROGRAMME READINESS
PROGRAMME READINESS SCORE (0-100)
HEADLINE KPIS
STORES IN SCOPE |  | ON TRACK / COMPLETE | AT RISK | BLOCKED
TOTAL OPEN ISSUES |  | AVG READINESS | STORES GO | STORES BLOCKED
PER-STORE READINESS SCORE
PER-CHECKPOINT COMPLIANCE (YES COUNT)
MANAGEMENT CALL-OUTS
Is the rollout on track?
Where is the worst region?
Which checkpoint is the weakest link?
Where is the issue concentration?

## Inputs
Franchise Rollout · Inputs
One row per store · campaign deployment audit · 8 compliance checkpoints · v2.0 · Investor-ready
STORES IN SCOPE
| ID | Store | Country / region | Franchisee | Assets received | Brief signed | Launch date set | Signage installed | Local PR briefed | Aggregator updated | CRM push live | Local promo activated | Open issue count | Status | Notes
| STR-001 | Sample Store 01 | Region A | Corporate | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0 | On track
| STR-002 | Sample Store 02 | Region A | Corporate | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Partial | 1 | On track
| STR-003 | Sample Store 03 | Region A | Franchisee A | Yes | Yes | Yes | Yes | Yes | Partial | No | No | 2 | At risk | CRM + promo not live
| STR-004 | Sample Store 04 | Region B | Franchisee B | Yes | Yes | Yes | Yes | Partial | Yes | Yes | Yes | 1 | On track
| STR-005 | Sample Store 05 | Region B | Franchisee B | Yes | Yes | Yes | Partial | No | Yes | Yes | Yes | 2 | At risk
| STR-006 | Sample Store 06 | Region B | Franchisee C | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0 | On track
| STR-007 | Sample Store 07 | Region C | Franchisee D | Yes | Yes | Partial | No | No | No | No | No | 4 | Blocked | Awaiting franchisee approval
| STR-008 | Sample Store 08 | Region C | Franchisee D | Yes | Yes | Yes | Yes | Yes | Yes | Partial | No | 1 | At risk
| STR-009 | Sample Store 09 | Region D | Franchisee E | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0 | On track
| STR-010 | Sample Store 10 | Region D | Franchisee F | Yes | Yes | Yes | Yes | Yes | Partial | Yes | Yes | 1 | On track
| STR-011 | Sample Store 11 | Region E | Franchisee G | Yes | Partial | Yes | No | No | No | No | No | 5 | Blocked | Brief not signed
| STR-012 | Sample Store 12 | Region E | Franchisee G | No | No | No | No | No | No | No | No | 6 | Blocked | Not started

## Calc
Calculations
Per-store readiness score · per-region rollup · issue count · v2.0 · Investor-ready
PER-STORE READINESS
| Store | Yes count | Partial count | Score (0-100) | Verdict
PER-REGION ROLLUP (TOP 8 REGIONS SEEN)
| Region | Stores | Avg score | On track | At risk / blocked
Region A
Region B
Region C
Region D
Region E
Region F
Region G
Region H
PER-CHECKPOINT COMPLIANCE
| Checkpoint | Yes | Partial | No
Assets received
Brief signed
Launch date set
Signage installed
Local PR briefed
Aggregator updated
CRM push live
Local promo activated
PROGRAMME READINESS SCORE (0-100)
Score

## Checks
Audit Checks
Rollout completeness gates · v2.0 · Investor-ready
AUDIT PANEL
| # | Check | Status | Value | Threshold | Action
| 1 | Every store has franchisee/owner |  |  | 0 | Set franchisee/owner per store.
| 2 | Every store has assets received |  |  | 0 | Assets not received — escalate today.
| 3 | Every store has brief signed |  |  | 0 | Brief not signed — escalate to franchisee lead.
| 4 | Programme score ≥ GO floor |  |  |  | Below GO floor — re-cut readiness with field team.
| 5 | No stores BLOCKED |  |  | 0 | Blocked stores need triage today.
| 6 | Total open issues ≤ tolerance |  |  |  | Issue count above tolerance — escalate.
| 7 | No duplicate store IDs |  |  |  | Duplicate IDs corrupt rollups.

## Scenarios
Scenario planning
Base · Conservative · Aggressive · v2.0 · Investor-ready
SCENARIO DRIVERS
| Driver | Base case | Conservative | Aggressive | Unit | Notes
| Stores in scope | 12 | 8 | 20 | Count
| Avg open issues / store | 2 | 4 | 1 | Count
| Brief sign-off cycle (days) | 7 | 14 | 3 | Days
READING THE SCENARIOS
Conservative stress-tests the plan against weaker demand, softer margins, and slower repeat behaviour. Aggressive shows the upside if execution lands. Drivers are intentionally few and load-bearing — change one and the dashboard recalculates. Use this tab in board and lender conversations to show downside cover and upside path.
DECISION RULES
| • | If we are tracking below the conservative case for two consecutive review cycles, escalate to the founder and trigger the conservative-case action plan.
| • | If we are tracking above the base case, do not unlock aggressive spend until the third consecutive review cycle confirms the trend.
| • | Document any change to a driver in the Document Control change log so reviewers can see what moved and why.

## Action_Plan
Action Plan
From insight to commitment to follow-through · v2.0 · Investor-ready
DECISIONS, OWNERS, DEADLINES
| # | Action / decision | Owner | Priority | Due date | Status | Expected impact
| 1 | Tighten weekly performance review cadence with operations lead | Marketing Lead | High | Next Monday | Open | Faster spotting of channel drift; reduces overspend risk
| 2 | Re-baseline CAC target against last 90 days; replace stale assumption | Founder | High | This week | In progress | Budget decisions that match current reality
| 3 | Audit delivery platform menu photography vs in-store standard | Brand Lead | Medium | Within 2 weeks | Open | Higher menu CTR; better delivery conversion
| 4 | Stand up monthly review pack using this workbook as the source | Ops Lead | Medium | Next 30 days | Open | Faster decisions, fewer reactive moves

## Assumptions
Assumptions
Drivers behind every formula in this workbook · edit blue cells only · v2.0 · Investor-ready
| Assumption | Value | Unit | Why it matters
| Reporting currency | AED | AED | Default is AED — replace if your reporting currency differs.
| Programme score GO floor | 85 | Score | Below this — programme not GO.
| Issue tolerance (total) | 10 | Count | Above this — escalate to leadership.
| Audit pass threshold | 85% | % | Sign-off threshold.
HOW TO READ THIS TAB
Blue cells are inputs you edit. Every other cell on this tab is a fixed reference. Change one driver here and the whole workbook recalculates — that is the point of this tab.
CELL COLOUR LEGEND
| INPUT |  | CALCULATED |  | LOCKED / REFERENCE | OK / GOOD | WATCH | CRITICAL

## Definitions
KPI Glossary & Definitions
One source of truth for every metric in this workbook · v2.0 · Investor-ready
DEFINITIONS
| Metric / Term | Definition | Formula / source
| Checkpoint | One of 8 deployment items per store. | Inputs
| Per-store score | (Yes + 0.5×Partial) / 8 × 100, minus 5 per open issue. | Calc
| Verdict | GO ≥ 85 · GO WITH CONDITIONS 70-84 · AT RISK 50-69 · BLOCKED < 50. | Calc
| Programme score | Average per-store score across all stores. | Calc

## README
Franchise Campaign Rollout Tracker
Ashmo · Restaurant Growth Toolkit · v2.0 · Investor-ready
PURPOSE
A franchise rollout governance tracker. For every store in scope, audits 8 deployment checkpoints (assets received, brief signed, launch date, signage, local PR, aggregator update, CRM push, local promo) and tracks open issues. Computes a per-store readiness score, per-region rollup, per-checkpoint compliance, and a single programme readiness score with GO / GO-WITH-CONDITIONS / AT-RISK / BLOCKED verdict — the standard view a franchise board needs.
BIG QUESTIONS THIS ANSWERS
| • | Are all stores ready for the campaign rollout?
| • | Where is the rollout blocked or at risk?
| • | Which region is the weakest link?
| • | Which checkpoint is the worst performer across stores?
| • | Where do we triage today?
WORKBOOK MAP
| Tab | What it's for
| Dashboard | Programme score, store readiness chart, checkpoint chart, callouts.
| Inputs | Per-store status across 8 deployment checkpoints + issue count.
| Calc | Per-store readiness, per-region rollup, per-checkpoint compliance, programme score.
| Checks | Brief / assets / blocked / issues gates.
| Scenarios | Headcount and budget shifts.
| Action_Plan | Decisions per store / region.
| Assumptions | Score floor, issue tolerance, regions.
| Definitions | Glossary.
| README | How to use end-to-end.
| Document_Control | Author, reviewers, change log.
HOW TO USE
| Step 1 | Set Assumptions: GO floor, issue tolerance.
| Step 2 | Update Inputs with each store's checkpoint status (Yes / Partial / No).
| Step 3 | Open Calc + Dashboard for per-store readiness and the programme score.
| Step 4 | Resolve REVIEW items on Checks before next steerco.
WHO THIS IS FOR
| • | Franchise teams running multi-unit rollouts.
| • | Brand and marketing leads ensuring campaign consistency.
| • | Operations leads holding stores to standard.
| • | Founders / CEOs reviewing programme health.
GOVERNANCE & INTEGRITY
| • | Replace sample stores before sharing externally.
| • | Update status weekly; escalate Blocked same-day.
| • | Document the campaign brief and asset pack location in the README.

## Document_Control
Document Control
Authorship · versioning · approvals · change log · v2.0 · Investor-ready
DOCUMENT IDENTITY
| Field | Value
| Workbook | Franchise Campaign Rollout Tracker
| Prepared by | Ashmo · Restaurant Growth Toolkit
| Owner (accountable) | Marketing Lead
| Version | 2.0
| Issued | 2026-05-14
| Review cadence | Monthly, or after a material business event
| Classification | Internal · Commercially sensitive
| Currency convention | Default AED — change in Assumptions tab if your reporting currency differs
| Source of truth | This workbook is the single source of truth for the metrics it contains
| Distribution | Internal management, board, lender / investor, franchise partners — as appropriate
REVIEWERS & APPROVERS
| Role | Name | Approval status | Comments
| Founder / CEO |  | Pending
| Operations Lead |  | Pending
| Finance Lead |  | Pending
| Brand / Marketing Lead |  | Pending
CHANGE LOG
| Date | Author | Version | Change summary
| 2026-05-14 | Ashmo Toolkit | 3.0 | v3 rebuild: currency-neutral, deeper domain logic, expanded checks, scorecards, sensitivity tables, and CEO/board callouts. Sample data is illustrative — replace with your own.