## Dashboard
Store Launch Dashboard
Phase progress · workstream health · risk register · go / no-go score · v2.0 · Investor-ready
LAUNCH READINESS
LAUNCH READINESS SCORE (0-100)
HEADLINE KPIS
TASKS TOTAL |  | COMPLETE | IN PROGRESS / BRIEFED | BLOCKED
AVG RISK |  | HIGH-RISK (≥4) | TOTAL BUDGET | % COMPLETE
PER-PHASE COMPLETION
PER-WORKSTREAM COMPLETION
MANAGEMENT CALL-OUTS
Are we go for launch?
What is blocked?
Where is risk concentrated?
How healthy is the day-1 trade plan?

## Inputs
Store Launch · Inputs
One row per task · phase · workstream · owner · deadline · risk · v2.0 · Investor-ready
LAUNCH TASKS
| ID | Phase | Workstream | Task | Owner | Due date | Effort (days) | Status | Risk (1-5) | Dependency | Cost | Notes
| LAU-001 | Pre-launch (90-30 days out) | Permits & legal | Trade licence approved | Operations | Day -75 | 5 | Complete | 1
| LAU-002 | Pre-launch (90-30 days out) | Landlord / mall | Signage approval from landlord | Operations | Day -60 | 3 | Complete | 1
| LAU-003 | Pre-launch (90-30 days out) | Construction & fit-out | Fit-out 70% complete | Project Mgr | Day -30 | 30 | In progress | 3 |  | 75000
| LAU-004 | Pre-launch (90-30 days out) | Equipment & supply | Equipment ordered + delivery scheduled | Operations | Day -45 | 10 | Complete | 2 |  | 45000
| LAU-005 | Pre-launch (90-30 days out) | Hiring & training | Manager hired and onboarded | HR | Day -45 | 15 | Complete | 2
| LAU-006 | Pre-launch (30-7 days out) | Hiring & training | Team trained on POS, menu, SOP | Manager | Day -14 | 10 | In progress | 3 | LAU-005
| LAU-007 | Pre-launch (30-7 days out) | Brand assets | Signage installed and approved | Brand | Day -14 | 3 | Briefed | 2 | LAU-002 | 4500
| LAU-008 | Pre-launch (30-7 days out) | Digital & GBP | GBP listing live, photos uploaded | Marketing | Day -10 | 2 | Briefed | 2
| LAU-009 | Pre-launch (30-7 days out) | Aggregator setup | Listings live on Aggregator A and B | Marketing | Day -7 | 5 | In progress | 4 | LAU-007 | 0
| LAU-010 | Pre-launch (30-7 days out) | Local marketing | Hyperlocal flyer drop in trade area | Field | Day -7 | 5 | Planned | 2 |  | 3500
| LAU-011 | Pre-launch (30-7 days out) | PR & influencer | Top 5 local creators briefed | Brand | Day -7 | 4 | Planned | 3 |  | 6500
| LAU-012 | Launch week | Day-1 trade plan | Soft-open day with team | Manager | Day -1 | 1 | Planned | 2 | LAU-006
| LAU-013 | Launch week | Day-1 trade plan | Grand-open with PR + creators | Marketing | Day 0 | 1 | Planned | 4 | LAU-011 | 18000 | Critical
| LAU-014 | Launch week | CRM & loyalty | Welcome offer push to CRM list | CRM | Day 1 | 1 | Planned | 2 |  | 1500
| LAU-015 | Launch week | Operations readiness | Daily standup + incident log | Manager | Day 0-7 | 7 | Planned | 2
| LAU-016 | Post-launch (week 1-4) | Operations readiness | Service quality audit (week 2) | Brand | Day 14 | 2 | Planned | 3 |  | 1500
| LAU-017 | Post-launch (week 1-4) | Local marketing | Sustained hyperlocal push | Field | Day 7-28 | 10 | Planned | 2 |  | 4000
| LAU-018 | Post-launch (week 1-4) | Digital & GBP | First batch of customer reviews requested | Manager | Day 14 | 2 | Planned | 2
| LAU-019 | Post-launch (month 2-3) | Operations readiness | Month-2 financial review with ops + finance | Finance | Day 60 | 1 | Planned | 2
| LAU-020 | Post-launch (month 2-3) | CRM & loyalty | Retention cohort check | CRM | Day 75 | 2 | Planned | 2

## Calc
Calculations
Per-phase + per-workstream completion · risk · readiness score · v2.0 · Investor-ready
PER-PHASE PROGRESS
| Phase | Tasks | Complete | Complete % | Avg risk
Pre-launch (90-30 days out)
Pre-launch (30-7 days out)
Launch week
Post-launch (week 1-4)
Post-launch (month 2-3)
PER-WORKSTREAM PROGRESS
| Workstream | Tasks | Complete | Complete % | High-risk tasks
Permits & legal
Landlord / mall
Construction & fit-out
Equipment & supply
Hiring & training
Brand assets
Local marketing
Digital & GBP
PR & influencer
CRM & loyalty
Aggregator setup
Operations readiness
Day-1 trade plan
RISK REGISTER (HIGH-RISK TASKS)
| Rank | Task | Workstream | Risk (1-5) | Status
1
2
3
4
5
6
7
8
LAUNCH READINESS SCORE (0-100)
Score

## Checks
Audit Checks
Launch readiness gates · v2.0 · Investor-ready
AUDIT PANEL
| # | Check | Status | Value | Threshold | Action
| 1 | Every task has owner |  |  | 0 | Set owner for every task.
| 2 | Every task has due date |  |  | 0 | Set due date for every task.
| 3 | No tasks blocked |  |  | 0 | Blocked tasks must be escalated immediately.
| 4 | All Permits & Legal complete by Day -7 |  |  | 0 | Permits NOT closed — launch is at legal risk.
| 5 | Aggregator setup complete by launch |  |  | 0 | Delivery channels not live — launch will under-trade.
| 6 | Day-1 trade plan complete |  |  | 0 | Day-1 trade plan tasks open — risk to opening day.
| 7 | Readiness score ≥ GO floor |  |  |  | Below GO floor — launch is high risk.
| 8 | Avg risk ≤ ceiling |  |  |  | Avg risk too high — escalate top items.

## Scenarios
Scenario planning
Base · Conservative · Aggressive · v2.0 · Investor-ready
SCENARIO DRIVERS
| Driver | Base case | Conservative | Aggressive | Unit | Notes
| Marketing budget | 50000 | 30000 | 80000 | AED
| Headcount on day 1 | 12 | 8 | 16 | People
| Day-1 trade target | 15000 | 8000 | 25000 | AED
| PR + influencer reach | 500000 | 250000 | 1000000 | Count
READING THE SCENARIOS
Conservative stress-tests the plan against weaker demand, softer margins, and slower repeat behaviour. Aggressive shows the upside if execution lands. Drivers are intentionally few and load-bearing — change one and the dashboard recalculates. Use this tab in board and lender conversations to show downside cover and upside path.
DECISION RULES
| • | If we are tracking below the conservative case for two consecutive review cycles, escalate to the founder and trigger the conservative-case action plan.
| • | If we are tracking above the base case, do not unlock aggressive spend until the third consecutive review cycle confirms the trend.
| • | Document any change to a driver in the Document Control change log so reviewers can see what moved and why.

## Action_Plan
Action Plan
From insight to commitment to follow-through · v2.0 · Investor-ready
DECISIONS, OWNERS, DEADLINES
| # | Action / decision | Owner | Priority | Due date | Status | Expected impact
| 1 | Tighten weekly performance review cadence with operations lead | Marketing Lead | High | Next Monday | Open | Faster spotting of channel drift; reduces overspend risk
| 2 | Re-baseline CAC target against last 90 days; replace stale assumption | Founder | High | This week | In progress | Budget decisions that match current reality
| 3 | Audit delivery platform menu photography vs in-store standard | Brand Lead | Medium | Within 2 weeks | Open | Higher menu CTR; better delivery conversion
| 4 | Stand up monthly review pack using this workbook as the source | Ops Lead | Medium | Next 30 days | Open | Faster decisions, fewer reactive moves

## Assumptions
Assumptions
Drivers behind every formula in this workbook · edit blue cells only · v2.0 · Investor-ready
| Assumption | Value | Unit | Why it matters
| Reporting currency | AED | AED | Default is AED — replace if your reporting currency differs.
| Readiness GO floor | 85 | Score | Below this — not GO.
| Avg risk ceiling | 2.5 | Score | Above this — escalate risk register.
| Audit pass threshold | 85% | % | Sign-off threshold.
HOW TO READ THIS TAB
Blue cells are inputs you edit. Every other cell on this tab is a fixed reference. Change one driver here and the whole workbook recalculates — that is the point of this tab.
CELL COLOUR LEGEND
| INPUT |  | CALCULATED |  | LOCKED / REFERENCE | OK / GOOD | WATCH | CRITICAL

## Definitions
KPI Glossary & Definitions
One source of truth for every metric in this workbook · v2.0 · Investor-ready
DEFINITIONS
| Metric / Term | Definition | Formula / source
| Phase | Pre-launch (90-30, 30-7) · Launch week · Post-launch (week 1-4, month 2-3). | Inputs
| Workstream | Permits, landlord, fit-out, equipment, hiring, brand assets, local marketing, digital, PR, CRM, aggregator, operations, day-1. | Inputs
| Risk | 1 = trivial · 5 = launch-blocking. Tracked per task. | Inputs
| Readiness score | 60% weighted on % complete, 20% on inverse avg risk, 20% on % not blocked. | Calc
| GO / NO-GO | ≥85 GO · 70-84 GO WITH CONDITIONS · 50-69 NO-GO REVIEW · <50 NO-GO. | Calc

## README
Store Launch Marketing Checklist
Ashmo · Restaurant Growth Toolkit · v2.0 · Investor-ready
PURPOSE
A launch control tower for opening a new store. Tasks are broken across 5 phases (90-30 days out, 30-7 days out, launch week, post-launch weeks 1-4, post-launch months 2-3) and 13 workstreams (permits, landlord, fit-out, equipment, hiring, brand assets, local marketing, digital + GBP, PR + influencer, CRM + loyalty, aggregator setup, operations readiness, day-1 trade plan). Rolls up to per-phase progress, per-workstream health, a top-8 risk register, and a single GO / NO-GO readiness score.
BIG QUESTIONS THIS ANSWERS
| • | Are we go for launch?
| • | What is blocked or at risk?
| • | Which workstream is the weakest link?
| • | Is the day-1 trade plan ready?
| • | What needs to be escalated this week?
WORKBOOK MAP
| Tab | What it's for
| Dashboard | Launch readiness score, headline KPIs, phase + workstream completion, callouts.
| Inputs | One row per task — phase, workstream, owner, due date, risk.
| Calc | Per-phase + per-workstream rollup, risk register, readiness score.
| Checks | Permits, aggregator, day-1 plan, score, risk gates.
| Scenarios | Headcount, marketing budget, opening week stress.
| Action_Plan | Decisions and follow-ups.
| Assumptions | GO floor, risk ceiling, opening day.
| Definitions | Glossary of every metric.
| README | How to use end-to-end.
| Document_Control | Author, reviewers, change log.
HOW TO USE
| Step 1 | Set Assumptions: GO floor, risk ceiling, opening date.
| Step 2 | Replace sample tasks with the launch-specific task list.
| Step 3 | Track status weekly; escalate blockers same-day.
| Step 4 | Review Dashboard at every weekly steerco.
| Step 5 | Resolve REVIEW items on Checks before signing GO.
WHO THIS IS FOR
| • | Founders / CEOs opening a new store.
| • | Operations leads driving the launch programme.
| • | Project managers coordinating workstreams.
| • | Investors funding new openings.
| • | Multi-unit teams standardising opening playbook.
GOVERNANCE & INTEGRITY
| • | Replace sample rows before sharing externally.
| • | Update task status weekly; escalate Blocked same-day.
| • | Document the opening date and trade plan in the README.

## Document_Control
Document Control
Authorship · versioning · approvals · change log · v2.0 · Investor-ready
DOCUMENT IDENTITY
| Field | Value
| Workbook | Store Launch Marketing Checklist
| Prepared by | Ashmo · Restaurant Growth Toolkit
| Owner (accountable) | Marketing Lead
| Version | 2.0
| Issued | 2026-05-14
| Review cadence | Monthly, or after a material business event
| Classification | Internal · Commercially sensitive
| Currency convention | Default AED — change in Assumptions tab if your reporting currency differs
| Source of truth | This workbook is the single source of truth for the metrics it contains
| Distribution | Internal management, board, lender / investor, franchise partners — as appropriate
REVIEWERS & APPROVERS
| Role | Name | Approval status | Comments
| Founder / CEO |  | Pending
| Operations Lead |  | Pending
| Finance Lead |  | Pending
| Brand / Marketing Lead |  | Pending
CHANGE LOG
| Date | Author | Version | Change summary
| 2026-05-14 | Ashmo Toolkit | 3.0 | v3 rebuild: currency-neutral, deeper domain logic, expanded checks, scorecards, sensitivity tables, and CEO/board callouts. Sample data is illustrative — replace with your own.